## Status Report
Project Name: Einstein
Today's date: June 15
Summary |  |  |  | Overall Status (RAG)
We have completed the Web Application Einstein to help Customer Support Executives track Information, Account details, Devices health check and billing & payments. |  |  |  | Green
Completed Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Design a mockup web app | June 1 -14 | Completed | Web Designer |  | The wireframe was completed on time
Get sign up from Stakeholders | June 15 - 17 | Completed | Project Manager |  | Design is approved
Develop a Web App | July 25 - Sept 20 | Completed | Developers |  | Web Development was completed
Testing | Sept 7 - Oct 11 | Completed | Testers |  | Testing, bug fixes and retesting was done effeciently
Push the code to Production environment and Test | Oct 12 - Nov 24 | Completed | Developers/Testers |  | Production environment deployment and testing went smooth enough
Upcoming Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
Unanticipated network and power outage |  | L | Considered Project Buffer for the schedule |  |  | PM

## ROAM
ROAM Analysis
| Issues | Actions | ROAM designation
Issue 1 | Unanticipated network and power outage | Considered Project Buffer for the schedule | Mitigated

## Retrospective
Retrospective: Einstein
2015-06-01
Project Summary:
Our plan is to develop Web Application for Customer Care Executives to deliver continuous support to the customers on the health of devices connected and detailed services provided to customers and all required information at one stop application.
Project Status:
Project Goals and Objectives: | Increase revenue by 10% by developing Einstein Web Application that helps customer care executives manage billing and health check of devices, by the end of the year.
Duration of project: | 6 Months (26 Weeks)
Team: | 6
Link to Project Doc(s) | [Links]
Methodology: | Agile/Scrum
Project Resources: | Developer, QA, Project Manager, Director, Primary Stakeholders
Lessons Learned
Things that went well:
Launched Web Application on scheduled time
Things that need improvement:
Consider vacation plans while doing capacity planning
Where we got lucky:
There was a power and network outage due to Tornado, hence we lost some time, but the team managed to cover-up with the due to Risk Mitigation plan and Project Buffer in place.
Action Items
What actions should we take as a result of our lessons learned?
Action Item | Type | Owner | Links
Continue to monitor results for additional improvements | Monitor | Project Manager | [Link]
Future Considerations
What would we recommend future projects of a similar nature mitigate or design contingency plans for?
Risk | Type | Contact | Link(s)
Capacity Planning is important | Time Risk | Project Manager | [Link]
Optional Supporting Materials and Notes
Retrospective Meeting Notes
Date: 15 June 2022
Owner: PM
Attendees: Developer, QA, Stakeholders