## OKR
OKR
O1 | Increase customer retention
KR1 | 25% of customers who were planning to leave due to bad services, were given product offers to retain
KR2 | 75% of customers surveyed
KR3 | 80% of customer care executives were re-examined and re-trained whenever needed
O2 | Continuously improve product and services
KR1 | Resolve 90% of support tickets by first quarter
KR2 | Billing and Payment options made efficient by third quarter
KR3 | Provide offers on secondary accounts and devices

## RACI
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Web Page Development | Manager | Graphic Designer | Web Developer | Quality Assurance Tester | Backend Developer | Web Designer
Task/Deliverable
Design Web App | A | C | I | I | I | R
Create mockup pages | A | C | C | I | C | R
Design image assets | I | R | I | I | I | A
Backend Development | A | I | I | I | R | I
Code/Develop | A | I | R | I | I | I
Test | A | I | C | R | I | I
Note on A1: Should this be "Execution phase?" -Elizabeth O'Hare
Note on B1: Remove only 1 task for Responsible -Cassie Maschhoff Also this doesn't match the stakeholders. Perhaps outdated? -Cassie Maschhoff