## WBS
WBS
Milestone | ID | Task | Owner | Duration (days) | Notes
Design Einstein Web App | 1.1 | Design a mockup web app | Web Designer | 10 | Create a wireframe of the Web App
| 1.2 | Get sign up from Stakeholders | PM | 3 | PM gets design sign off
| 1.3 | Design a web app | Web Designer | 25 | Design the UI of Web App
Develop a Web App | 2.1 | Code/develop a web app | Front End Developer | 30 | Develop the web app
| 2.2 | Backend Service development | Backend Developer | 25 | Connect to DB and create APIs
| 2.3 | System Integration | Developer | 10 | Front-End and Backend Integration
| 2.4 | Unit Tests | Developer | 7 | Workflow tests
Testing | 3.1 | Test plan/test scenarios | Tester | 10 | Write test plan and test setup
| 3.2 | UI/UX testing | Tester | 5 | UI/UX testing
| 3.3 | Backend testing | Tester | 5 | DB and API testing
| 3.4 | Retesting on defect fixes | Tester | 5 | Retesting bug fixes as and when required
Production environment | 4.1 | Push code to Production Environment | Developer | 15 | Push code to Production Environment
| 4.2 | Test in Production Environment | Tester | 10 | Test in Production Environment
| 4.3 | Bug fixes | Developer | 5 | Bug fixes
| 4.4 | Bug resting | Tester | 5 | Bug resting