## Gantt Chart
Gantt Chart
TITLE: Einstein | [6 empty] | COMPANY NAME:
PROJECT MANAGER: [Name] | [6 empty] | CREATION DATE: |  |  |  |  | 06/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [37 empty] | PHASE TWO | [41 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26
[7 empty] | June | [21 empty] | July | [20 empty] | August | [22 empty] | September | [21 empty] | October | [20 empty] | November
[7 empty] | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T
1 | Design Einstein Web App | [5 empty] | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24
1.1 | Design a mockup web app | Web Designer | 6/1 | 6/14 | 10 | 100% | bar: June W 1 to June T 14
1.2 | Get sign up from Stakeholders | PM | 6/15 | 6/17 | 3 | 100% | bar: June W 15 to June F 17
1.3 | Design a web app | Web Designer | 6/20 | 7/22 | 25 | 100% | bar: June M 20 to July F 22
2 | Develop a Web App
2.1 | Code/develop a web app | Front End Developer | 7/25 | 8/31 | 30 | 100% | bar: July M 25 to August W 31
2.2 | Backend Service development | Backend Developer | 8/1 | 8/31 | 25 | 100% | bar: August M 1 to August W 31
2.3 | System Integration | Developer | 9/1 | 9/14 | 10 | 100% | bar: September T 1 to September W 14
2.4 | Unit Tests | Developer | 9/12 | 9/20 | 7 | 100% | bar: September M 12 to September T 20
3 | Testing
3.1 | Test plan/test scenarios | Tester | 9/7 | 9/20 | 10 | 100% | bar: September W 7 to September T 20
3.2 | UI/UX testing | Tester | 9/21 | 9/27 | 5 | 100% | bar: September W 21 to September T 27
3.3 | Backend testing | Tester | 9/28 | 10/4 | 5 | 100% | bar: September W 28 to October T 4
3.4 | Retesting on defect fixes | Tester | 10/5 | 10/11 | 5 | 100% | bar: October W 5 to October T 11
4 | Production environment
4.1 | Push code to Production Environment | Developer | 10/12 | 11/1 | 15 | 100% | bar: October W 12 to November T 1
4.2 | Test in Production Environment | Tester | 11/2 | 11/15 | 10 | 100% | bar: November W 2 to November T 15
4.3 | Bug fixes | Developer | 11/11 | 11/17 | 5 | 100% | bar: November F 11 to November T 17
4.4 | Bug resting | Tester | 11/18 | 11/24 | 5 | 100% | bar: November F 18 to November T 24