## Comm Plan Exemplar
Project Einstein: Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm IST | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Retrospective | Status Update | One time | Project Manager | Last day of Sprint at 6pm IST | In Person | Update lessons learnt, better approaches to be followed | [link to meeting agenda and notes] | Appreciations and celebrations also be part of this meeting to encourage team members and help team bonding
1:1s with Core Team | Informational Update | Weekly | Project Manager | Different Times with each team member | In Person | To resolve barriers and encourage career growth | [link to meeting agenda and notes] | If needed, check with the manager for better opportunities for career growth or related issues
My Manager | Status Update | Weekly | Project Manager | Monday afternoons at 2pm IST | In Person | Update on event planning, ask questions, and get feedback | [link to meeting agenda and notes] | Come prepared with a brief update and specific questions
Core Team- Surveys | Survey | One time | Project Manager | Agreed upon time | Email (from company address) | Address issues and bring improvements in the process and team | [link to meeting agenda and notes] | Conflict resolution and other issues can be sometimes addressed by Anonymous feedback
Senior Leaders: Director of Product and higher management | Status Update | One time | Project Manager | Debrief the week after the event | Email (from company address) | High-level information and general updates | [link to folder with training notes and survey results]